## Solution
Gantt chart: 10 activities with precedence (SOLUTION)
Activity | Predecessors | Duration (days) | Start | End
A | - | 40 | 0 | 40
B | - | 20 | 0 | 20
C | A, B | 15 | 40 | 55
D | A | 25 | 40 | 65
E | C | 15 | 55 | 70
F | A, B | 25 | 40 | 65
G | F | 10 | 65 | 75
H | G | 15 | 75 | 90
I | G | 10 | 75 | 85
J | I | 15 | 85 | 100
Project completion time (days) |  |  |  | 100
Critical path: A > F > G > I > J (40 + 25 + 10 + 10 + 15 = 100 days)

## Practice
Gantt chart: 10 activities with precedence (PRACTICE)
Yellow cells = fill them yourself. Row A is already done as an example. Start = biggest End of its predecessors (0 if none). End = Start + Duration.
Activity | Predecessors | Duration (days) | Start | End
A | - | 40 | 0 | 40
B | - | 20
C | A, B | 15
D | A | 25
E | C | 15
F | A, B | 25
G | F | 10
H | G | 15
I | G | 10
J | I | 15
Project completion time (days)
Hint: use =MAX(E5:E14) in the yellow cell.